## Sheet1
Work Breakdown Structure
Project Name: OMEGA
Project Leader: Varad Chaskar
Requirement | Hardware | Software | Enclosure & Cloud | Web & App Develop. | AI and ML | Managenement
Document containing list | A document containing | Flowchart of the | Achitecture Diagram | Design of Web | Design of AI model | Create Project
of all requirements | Modifications summary | Sensor Module |  | Wireframe |  | Proposal
list of problems in the | Data Sheets Collection | Flowchart of the | Create 3D design of | Write code for HTML | Development of AI | Create Project
pH sensor | of the Components | Actuator Module | the Sensor Module | Slider | model | Charter
List of problems present | Breadboard Design of | Code for the | Create 3D design of | Write code for HTML | Performance parameter | Create Work Breakdown
in the nutrient sensor | the Sensor Module | Sensor Module | the Actuator Module | Button | plotting | Structure Chart
Collection of news | Breadboard Design of | Code for the |  | Documentation of | Evaulation of AI | Create and maintain
articles for advantages | the Actuator Module | Actuator Module | the UPS module | Adjustable Slider | model | meeting minutes
Why hydroponic | Breadboard Design of | Documentation of code |  | Documentation of | Deployment and | Create and maintain
automation fails? | the UPS Module | for Sensor Module | hydroponic tank | Button | integration to web | GANTT chart
Nutrient required for | Schematic Design of | Documentation of code |  | List of all features of | Screenshots of | Create Expense Reports
plant according growth | the Sensor Module | for Actuator Module | netpot | Webpage | AI Model
Need and difference with | Schematic Design of | Testing Plans for | Screenshots of AWS | Screenshots of |  | Screenshots of Asana
UV light | the Actuator Module | both Modules | cloud and Thingspeak | Webpage
Need and difference with | PCB Design of the | Test cases of the
air pump | Sensor Module | Sensor Module
| PCB Design of the | Test cases for the
| Actuator Module | Actuator Module
Make Component list of
the Sensor Module
Make Component list of
the Actuator Module
Create Bill of Materials
of whole project